## SWDEV-Estimate
SOFTWARE DEVELOPMENT - PROJECT ESTIMATE
Activity: | Advising System |  | Rules: no cell > 40 hrs; no line's sub-total > 100 hrs
Estimator: | Nathan Cox & Christian Walker |  | (if so, break down into smaller tasks)
Number | Development Task | Design | Code | Debug | Test | Overhead | Sub-Total | Contingency | TOTAL
1 | Multi-Permissions Views | 2 | 5 | 2 | 2 |  | 11 | 8.25 | 19.25
2 | External Links and Resources | 1 | 1 | 1 | 1 |  | 4 | 3 | 7
3 | Interactive Schedule Grid | 8 | 21 | 8 | 5 |  | 42 | 31.5 | 73.5
4 | Form Creation | 4 | 1 | 1 | 1 |  | 7 | 5.25 | 12.25
5 | Add Edit/View/Delete Schedule Button Logic | 2 | 4 | 2 | 1 |  | 9 | 6.75 | 15.75
6 | Course Search Algorithm | 1 | 1 | 1 | 1 |  | 4 | 3 | 7
7 | Implement Course Search Results View | 4 | 6 | 3 | 2 |  | 15 | 11.25 | 26.25
8 | Implement Course View | 4 | 4 | 2 | 1 |  | 11 | 8.25 | 19.25
9 | Implement "Edit" Course View | 2 | 6 | 3 | 2 |  | 13 | 9.75 | 22.75
10 | Audit Logs | 2 | 4 | 2 | 2 |  | 10 | 7.5 | 17.5
11 | Degree Evaluation Algorithm | 2 | 4 | 2 | 1 |  | 9 | 6.75 | 15.75
12 | Course and Schedule Comments | 2 | 8 | 4 | 2 |  | 16 | 12 | 28
13 | Student Email Notifications | 2 | 3 | 2 | 1 |  | 8 | 6 | 14
14 | LDAP Access | 4 | 8 | 4 | 2 | 1 | 19 | 14.25 | 33.25
15 | Change Account Credential | 2 | 4 | 2 | 1 |  | 9 | 6.75 | 15.75
16 | Error and Retry Logic | 4 | 6 | 4 | 2 |  | 16 | 12 | 28
17 | Visual Feedback through Color Coding | 2 | 3 | 2 | 1 |  | 8 | 6 | 14
18 | Credit Tracking | 2 | 4 | 2 | 1 |  | 9 | 6.75 | 15.75
19 | Help Pages | 4 | 4 | 2 | 1 | 1 | 12 | 9 | 21
20 | Implement About Screen to Show Version Info | 1 | 1 | 1 | 1 |  | 4 | 3 | 7
21 | Screen Timeout | 1 | 2 | 1 | 1 |  | 5 | 3.75 | 8.75
22 | [6 empty] | 0 | 0 | 0
23 | [6 empty] | 0 | 0 | 0
24 | [6 empty] | 0 | 0 | 0
25 | [6 empty] | 0 | 0 | 0
| SUBTOTAL: | 56 | 100 | 51 | 32 | 2 | 241 | 180.75 | 421.75
| CONTINGENCY: | 42 | 75 | 38.25 | 24 | 1.5 | 180.75
| TOTAL: | 98 | 175 | 89.25 | 56 | 3.5 | 421.75

## SWDEV-Weighting
SOFTWARE DEVELOPMENT - PROJECT ESTIMATE - CONFIDENCE WEIGHTING
Activity: | Advising System
Estimator: | Nathan Cox & Christian Walker
|  | MINIMUM | EXPECTED | MAXIMUM
| CONFIDENCE FACTOR (%) | 25 | 50 | 100
PROJECT |  |  | 1
| Scope Definition |  |  | 1
| Complexity of Project |  |  | 1
| Similarity to Other Projects |  |  | 1
| Fast-track Schedule |  |  | 1
| Schedule Flexibility |  |  | 1
ENVIRONMENT
| Experience of Resources Required for Project | 1
| Availability of resources required for project |  | 1
| Customer Flexibility |  | 1
| Customer Knowledge of Needs |  | 1
ESTIMATE
| Experience of Estimator |  | 1
| Time Allowed for Estimating |  | 1
| Estimator Same as Implementor |  |  | 1
RESOURCES
| Level of domain knowledge required |  | 1
| Complexity of Logic |  |  | 1
| Core supporting modules required |  |  | 1
| Number of Variables per Column | 1 | 6 | 8
| Total Number of Variables (Calc'd by # of entries in column B8-B31) | 15 | 15 | 15
TOTAL
| TOTAL WEIGHTED AVERAGE: | 1.6667 | 20 | 53.3333 | 75